CROSSOVER TRAFFIC CONTROL [618] (REVISED 12-4-25 M)

Description. This work includes furnishing, installing, maintaining, and removing traffic signs, barricades, lights, signals, pavement markings, and other specified traffic control devices on contracts utilizing crossovers.

Materials. Furnish materials that meet Subsection 618.02.

Construction Requirements. Provide traffic control in accordance with Section 618. Furnish a traffic control plan in accordance with Subsection 618.03.2.

Traffic Control – Crossover. Construct and sign crossovers as specified in the contract, including plan details and Detailed Drawing 618-30. Remove existing striping, re-stripe, and sign for first phase of the cross-over. Upon completion of that phase of work, remove striping, re-stripe and sign for the opposite phase.

Traffic Control – Two-Way Traffic. Install signage and striping, and divide traffic between crossovers in accordance with contract requirements. Furnish and install surfaced mounted, hinged flexible guideposts for two-way traffic operations. Install 36-inch tall flexible, self-erecting delineators capable of withstanding numerous impacts from any direction without splitting, breaking, or detaching from the base or the surface to which the base is attached. Replace and reset any flexible delineator(s) that fail to meet these performance requirements.

Traffic Control. Install all other traffic control devices required for work not performed under crossover conditions, and for any additional traffic control or signage not shown in the plans, in accordance with the contract requirements.

Sequencing. Complete all work within the closed section of roadway during crossover operations. This includes but is not limited to bridge work, plant mix paving, milling, guardrail installation, pavement markings, rumble strips, and signing. Complete all work to the satisfaction of the Project Manager prior to switching traffic. Return traffic to its normal traffic configuration within 24 hours of completing work.

The Department will deduct $10,000 per calendar day for any crossover left in place without active work occurring within the closed section of roadway.

Traffic control installed to reduce traffic to a single lane for facilitating work in areas where a crossover was utilized will not be measured for payment.

After completing all phases of work, ensure all striping and pavement markings for the crossover configuration have been removed and apply epoxy traffic paint to all mainline pavement markings in their final configuration. Ensure pavement markings are completed to the satisfaction of the Project Manager.

Method of Measurement.

Traffic Control – Crossover. Each phase of crossover traffic control is measured as one Traffic Control – Crossover unit and includes the furnishing, installing, maintaining and removal of traffic control devices, pavement markings, striping, and the replacement of all damaged devices.

Traffic Control – Two-Way Traffic. Two-way traffic control is measured by the mile (kilometer) along the double yellow striping and includes the furnishing, installing, maintaining and removal of traffic control devices, pavement markings, striping, and all replacement of damaged devices.

Traffic Control. Traffic control required for work performed while traffic is not on crossovers (except as noted above) or for additional work not shown in the contract will be measured by the unit used and accepted according to the value shown in the “Traffic Control Rate Schedule.”

Epoxy traffic paint will be measured and paid for in accordance with Section 620.

Basis of Payment. Payment for the completed and accepted quantities is made under the following:

| Pay Item | Pay Unit |
| --- | --- |
| Traffic Control – Crossover | Each |
| Traffic Control – Two-Way Traffic | Mile (kilometer) |
| Traffic Control | Unit |