## Notes
Each row has a number associated with an activity in order for the filter to work. To reduce noise in the worksheet numbers below the first row are formatted with white text. To see effect, add a colored fill to this column.
The worksheet has activities from both the Consultant Design Flowchart and the Consultant Wetland Mitigation Design Flowchart combined.
The subtotal function is used for subtotals as a more efficient function then the sum function. If there are other subtotals within ref1:ref2 (or nested subtotals), these nested subtotals are ignored to avoid double counting.
SUBTOTAL(function_num, ref1:ref2) When function_num=9, the subtotal function sums all the rows including hidden rows. The subtotal function ignores any rows that are not included as the result of a filter, no matter which function_num value you use.
Survey Crew: Past estimate shells had a column for survey/drill crew. The hours input represented a crew of two people with the following rate also representing two people. This did not align with the rest of the spread sheet or how Consultants calculated hours for survey. In addition this column applied to a limited number of activities. Therefore the column has been changed to "other" to allow more flexibility for its use. In addition, the hours input are for one person to be consistent with the rest of the spread sheet.

## Estimate
PROJECT: |  |  |  |  | PREPARED BY:
UPN: |  |  |  |  | DATE: |  | 2024-12-31
Activity | Tasks | Total Hours | Principal | Proj. Mgr. | Proj. Eng. | Design Eng. | CADD Tech. | Other | Clerc.
100.01 | PFR or PRF/SOW Report Development
100.01 | Attend Scoping Meeting | 0
100.01 | Determine project activities, and schedule | 0
100.01 | Press Release | 0
100.01 | Prepare/Submit Preliminary Field Review Report/SOW Report | 0
100.01 | Prepare Cost Estimate | 0
100.01 |  | 0
100.01 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.03 | Preliminary Project Development
100.03 | Control Survey | 0
100.03 | Cadastral Survey | 0
100.03 | Engineering Survey | 0
100.03 | ROW Research | 0
100.03 | Utility Coordination | 0
100.03 | Preliminary Plans Preparation | 0
100.03 | QA/QC of Deliverables | 0
100.03 |  | 0
100.03 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | ENVIRONMENTAL ENGINEERING ANALYSES REPORT
111 | Submit Draft Engineering Analyses Report | 0
111 | Submit Final Engineering Analyses Report | 0
111 |  | 0
111 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | Cultural Resource Report
177 | Draft Cultural Resource Report | 0
177 | Final Cultural Resource Report | 0
177 |  | 0
177 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | Hazardous Materials/Substances and Water Quality ISA
181 | Draft ISA checklist or report | 0
181 | Final ISA checklist or report | 0
181 |  | 0
181 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | Biological Resource Report/Biological Assessment
182 | Draft Biological Report | 0
182 | Final Biological Report | 0
182 |  | 0
182 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.18 | Prepare R/W Documents
142 | Determine Final Construction Limits | 0
142 | Complete Final R/W Documents | 0
142 | Review Cost Estimates for R/W | 0
142 |  | 0
142 |  | 0
142 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.04 | Preliminary Plan Review
100.04 | Track Comments, Comment/Response Document | 0
100.04 |  | 0
100.04 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | PRELIMINARY ENVIRONMENTAL DOCUMENT OR CATEGORICAL EXCLUSION/SECTION 4(f) EVALUATION
116 | Develop Categorical Exclusion | 0
116 | Develop Preliminary Environmental Document or Preliminary Categorical Exclusion | 0
116 | Section 4(f) Evaluation | 0
116 |  | 0
116 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | Prepare SOW Report (Skip if PFR/SOW Report is Complete)
128 | Prepare/Submit Scope of Work Report | 0
128 | Prepare Cost Estimate | 0
128 |  | 0
128 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.05 | Prepare SOW Approval Report
100.05 | Track Comments, Comment/Response Document | 0
100.05 | Prepare Final SOW Approval Report | 0
100.05 |  | 0
100.05 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.06 | Final Project Development
100.06 | Pickup Survey | 0
100.06 | Final Design | 0
100.06 | Finalize Sections, cross sections and Details | 0
100.06 | Final Cost Estimate | 0
100.06 | Develop Project Manual | 0
100.06 |  | 0
100.06 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.07 | Final Plan Review
100.07 | Send Final Plans, Specs and Cost Estimate to MDT | 0
100.07 | Final Plan Review Meeting | 0
100.07 | Track Comments, Comment/Response Document | 0
100.07
100.07 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.08 | Complete Env. Permits and Utility Agreements
100.08 | Complete Env. Permits and Utility Agreements | 0
100.08 |  | 0
100.08 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.09 | Local Certification/Env. Permits/Utilities
100.09 | Local Certification/Env. Permits/Utilities | 0
100.09 |  | 0
100.09 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.13 | R/W Appraisal and Acquisition
100.13 | ROW Appraisal and Acquisition | 0
100.13 |  | 0
100.13 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.14 | R/W Certification Submittal
100.14 | ROW Certification | 0
100.14 |  | 0
100.14 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.12 | Final Plan Review Comment Response
100.12 | Revise Plans after Final Plans Review | 0
100.12 | Update Cost Estimate/Special Provisions | 0
100.12 | Comment Response Document | 0
100.12 | QA/QC of Deliverables | 0
100.12 |  | 0
100.12 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100.18 | Local Bid Letting
100.18 | Prepare Bid Packages and Advertise | 0
100.18 | Conduct Pre-Bid Meeting | 0
100.18 | Questions and Addenda | 0
100.18 | Bid Opening & Bid Tabs | 0
100.18 |  | 0
100.18 | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DESIGN PHASE ACTIVITIES | TOTAL DESIGN PHASE HOURS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DESIGN PHASE ACTIVITIES | Contract Administration | 0
DESIGN PHASE ACTIVITIES |  | 0
DESIGN PHASE ACTIVITIES | SUBTOTAL (HOURS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Hours | Total Project Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Summary
PROJECT: |  |  |  | PREPARED BY:
UPN: |  |  |  | DATE: |  | 2024-12-31
COST SUMMARY
|  | Hours | % of total | Rate |  |  | Extension
| Principal | 0 | #DIV/0! |  |  |  | 0
| Project Manager | 0 | #DIV/0! |  |  |  | 0
| Project Engineer | 0 | #DIV/0! |  |  |  | 0
| Design Engineer | 0 | #DIV/0! |  |  |  | 0
| CADD/Designer | 0 | #DIV/0! |  |  |  | 0
| Other | 0 | #DIV/0! |  |  |  | 0
| Clerical | 0 | #DIV/0! |  |  |  | 0
| TOTAL HOURS | 0
|  |  | LABOR SUBTOTAL |  |  |  | 0
GENERAL OVERHEAD @ |  | 1.7 | OVERHEAD SUBTOTAL |  |  |  | 0
TOTAL LABOR/OVERHEAD | [6 empty] | 0
DIRECT NONLABOR
| Miscellaneous (Blueline prints, mylars, multilith paper, telephone, postage, misc. equipment rental, maps, photos, survey mtls., display boards, etc.) | [5 empty] | 0
| Computer | Hours |  | Per Hour | 10 |  | 0
| Title commitments | Parcels |  | Per Parcel | 400 |  | 0
| Vehicle Rental | Days |  | Per Month | 271 | GSA | 0
| Mileage | Miles |  | Per Mile | 0.7 | GSA | 0
| Airline Trips | Trips |  | Per Trip | 600 |  | 0
| Lodging | Days |  | Per Day | 118.8 | GSA | 0
| Meals (full day) | Days |  | Per Day | 68 | GSA | 0
| Meals (1st and last day) | Days |  | Per Day | 51 |  | 0
Other
TOTAL DIRECT NON-LABOR | [6 empty] | 0
OUTSIDE SERVICES AND SUBCONTRACTS
R/W Appraisals, Negotiation & Acquisition
Soils/Geotechnical Survey/Report/Testing
Cultural Resource Studies/Report
Noise Study
Traffic Study/Report
Biological Resources Studies/Report
Surveys
Subsurface Utility Engineering (Phase lI)
Hazardous Materials (Initial Site Assessment)
Landscaping Plans
Electrical/Lighting Signalization etc.
Aerial Photography/Mapping
Other
Drilling Contractor
TOTAL OUTSIDE SERVICES AND SUBCONTRACTS | [6 empty] | 0
RECAPITULATION
| Total Labor/Overhead | [5 empty] | 0
| Total Direct Non-Labor | [5 empty] | 0
| Total Outside Services & Subcontracts | [5 empty] | 0
| Profit (12% of Total Labor Costs) | [5 empty] | 0
TOTAL ESTIMATED COST | [6 empty] | 0
Note on D22: Author: Check total hours matches total hours from previous page
Note on D24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use the consultants approved overhead rate. 1.7 is used as a placeholder.
Note on G31: Author: GSA does not have a daily vehicle rental rate. They use the monthly rate divided by 30.
Note on G32: Author: For privately owned vehicle. Mileage is less for rental vehicle.
Note on G34: Author: GSA + Tax. Standard Rate Shown
Note on G35: Author: Standard GSA rate shown
Note on G36: Author: GSA only allows for 75% of per diem on first and last day of travel.
Note on J62: Author: Adjust formula if Profit is other than 12%